## Risk log
Risk Register
Project name: QAC Project
Project manager: Gabriel
ID | Date Assigned | Risk description | Likelihood of the risk occurring. | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens.
1 | 2020-04-08 | Project schedule is not clearly defined or understood. | Low | Medium | Medium | Project Manager | Hold scheduling workshops with the project team so they understand the plan and likelihood of missed tasks is reduced. | Share the plan and go through upcoming tasks at each weekly project progress meeting.
2 | 2020-04-08 | Risks with the hardware and software (the development platform) chosen to perform project development. e.g., can this hardware and software handle the workload required to complete the project?. | Medium | High | High | Project Manager | Before starting the project, make sure that the machine and OS system are up to date to maximise productivity. Contact project board for the latest equipment. | Communicate the issue with the board about potential funding for new hardware/software to continue with the project.
3 | 2020-04-08 | Risks associated with personnel assigned to the project who may be pulled off any time for another assignment. | Low | High | High | Project Manager | Ensure that there is no other project set in place by the board before committing/starting the one at hand. | Ensure work is fully documented and has comments so whoever takes over the project can pick up from where it stopped.
4 | 2020-04-08 | Unplanned work that must be accommodated. | Low | High | Medium | Project Manager | Attend project scheduling workshops. Document all assumptions made in planning and communicate to the project manager before the start of the project. | Escalate to the Project Manager with plan of action, including impact on time, cost and quality.
5 | 2020-04-08 | Lack of communication, causing lack of understanding about the project. | Medium | Medium | Medium | Project Manager | Hold regular project meetings and review the project plan for potential areas of conflict. Use most appropriate channel of communication for audience e.g. don't send 3 paragraph email to Developers, have a call instead. | Correct misunderstandings immediately. Clarify areas that are not clear swiftly with project board.
6 | 2020-04-08 | Scope creep. | Medium | High | High | Project Manager | Understand the project goals from the start. Using a project management software such as Trello, make sure that all user stories are relevant and up to date. | Refer back to the original project plan and check if the work is align with this.
7 | 2020-04-08 | Added workload or time requirements because of new direction or policy. | Low | Medium | Medium | Project Manager | No ability to reduce likelihood. | Consider working extra hours in order to reach these new requirements whilst informing the project owner.
8 | 2020-04-08 | If the hardware and software products are prone to bugs and are “slow”, they may be inappropriate for developing a system. This can affect development, especially during the coding and testing stages. | Medium | Medium | Medium | Project Manager | Ensure that the machine(s) being used for the project has the most up to date anti virus software/firewall to prevent it from malware. Also make sure machine is filled with unnecessary applications taking up storage. | Run the anti-virus software which is installed on the machine to get rid of bugs to optimise the performance.
9 | 2020-04-08 | Theft of materials, intellectual property or equipment. | Low | High | High | Project Manager | Verify all physical security measures in place, such as locking of doors and windows when absent from workspace. | Notify appropriate authorities e.g. police, project board and initiate internal investigations.
10 | 2020-04-08 | Acts of God for example, extreme weather, leads to loss of resources, materials, premises etc.. | Low | High | High | Project Manager | Ensure home insurance in place. Familiarise project team with emergency procedures. Whenever it is possible, put back up systems in place. | Notify appropriate authorities. Follow health and safety procedures. Notify stakeholders and Project Board.

## Severity Table
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High

## Dropdowns
High
Medium
Low